## Schedule
|  |  | Schedule (sorted by Start date) |  | Week |  | Week |  | Week |  | Week |  | Week |  | Week |  |  | Week
Start | End | Seq | Task | Owner | -6 |  | -5 |  | -4 |  | -3 |  | -2 |  | -1 |  | 0 | +1 |  | Rulebook
1 | 2 | 1 | Select Contest Chair | VP Education | S | F
1 | 2 | 2 | Obtain Budget approval from Club Officers | Contest Chair | S | F | [13 empty] | x
3 | 3 | 3 | Create To-do/checklist/timetable (see Tasks sheet) | Contest Chair |  |  | SF
3 | 3 | 4 | Set date, time, and place. Hold contest in place of a regular meeting | Contest Chair |  |  | SF | [12 empty] | x
3 | 4 | 5 | Read ref. documents - http://www.tmd55.org/info-for-contest-organizers.html | Contest Chair |  |  | S | F
3 | 4 | 6 | Select Chief Judge | Contest Chair |  |  | S | F | [11 empty] | x
3 | 4 | 7 | Select Awards Owner | Contest Chair |  |  | S | F
3 | 4 | 8 | Select Refreshments Owner | Contest Chair |  |  | S | F
3 | 6 | 9 | Invite Toastmaster Dignitaries and Guests | Contest Chair |  |  | S | x | x | F
3 | 8 | 10 | Order and receive or download contest materials from TI | Contest Chair |  |  |  | S | x | x | x | F | [7 empty] | x
4 | 8 | 11 | Recruit and select judges. Network / trade with other clubs | Chief Judge |  |  |  | S | x | x | x | F
4 | 11 | 12 | Promote the club contest with enthusiasm and optimism | Contest Chair |  |  |  | S | x | x | x | x | x | x | x | F |  |  |  | x
5 | 5 | 13 | Create a draft agenda | Contest Chair |  |  |  |  | SF | [10 empty] | x
5 | 5 | 14 | Train Chief Judge if necessary, and review tasks and ownership | Contest Chair |  |  |  |  | SF
5 | 5 | 15 | Meet with Chief Judge to review tasks and ownership | Contest Chair |  |  |  |  | SF
5 | 7 | 16 | Select Toastmaster | Contest Chair |  |  |  |  | S | x | F
6 | 6 | 17 | Create a flier | Contest Chair | [5 empty] | SF
6 | 6 | 18 | Meet with Awards owner to plan gifts, awards, and trophies | Contest Chair | [5 empty] | SF | [9 empty] | x
6 | 7 | 19 | Select Test Speaker (Evaluation Contest). Network with other clubs | Contest Chair | [5 empty] | S | F
6 | 7 | 20 | Select Sergeants-at-Arms | Contest Chair | [5 empty] | S | F
|  |  | Select Check-in / Registration chair | Contest Chair | [5 empty] | S | F
6 | 7 | 21 | Select Ballot Counters | Chief Judge | [5 empty] | S | F | [8 empty] | x
6 | 7 | 22 | Select Timers | Chief Judge | [5 empty] | S | F | [8 empty] | x
6 | 9 | 23 | Confirm judge eligibility. Find new judges as needed | Chief Judge | [5 empty] | S | x | x | F
7 | 9 | 24 | Confirm contestant eligibility with TI | Contest Chair | [6 empty] | S | x | F | [6 empty] | x
7 | 9 | 25 | Order blank certificates | Awards Owner | [6 empty] | S | x | F
7 | 10 | 26 | Order and receive or make trophies and gifts | Awards Owner | [6 empty] | S | x | x | F
8 | 8 | 27 | Notify Contestants of Contest details; send rulebook and forms | Contest Chair | [7 empty] | SF | [7 empty] | x
8 | 8 | 28 | Notify Contest Officials of Contest details (date, time, place) | Chief Judge | [7 empty] | SF | [7 empty] | x
9 | 10 | 29 | Plan the Contestant briefing (use on-line script) | Contest Chair | [8 empty] | S | F
9 | 10 | 30 | Plan the Chief Judge briefing (use on-line script) | Chief Judge | [8 empty] | S | F
9 | 10 | 31 | Meet with the Refreshments owner to plan the refreshments | Contest Chair | [8 empty] | S | F
9 | 11 | 32 | Train judges if necessary | Chief Judge | [8 empty] | S | x | F
9 | 11 | 33 | Personalize on-line Toastmaster Script (found on District website) | Toastmaster | [8 empty] | S | x | F
10 | 11 | 34 | Organize forms and awards into folders by person | Contest Chair | [9 empty] | S | F
10 | 11 | 35 | Create/print/copy Agenda/Program document | Contest Chair | [9 empty] | S | F |  |  |  |  | x
10 | 11 | 36 | Personalize certificates | Chair/C.Judge | [9 empty] | S | F
10 | 11 | 37 | Plan for miscellaneous items (e.g. stop watches). Materials tab | Contest Chair | [9 empty] | S | F
10 | 12 | 38 | Reminder to Contestants | Contest Chair | [9 empty] | SF |  | SF
10 | 12 | 39 | Reminder to Contest Officials | Chief Judge | [9 empty] | SF |  | SF
11 | 13 | 40 | Identify volunteers/purchase and bring refreshments | Refresh Owner | [6 empty] | S | x | x | x | x | x | F
12 | 12 | 41 | Prepare for your role as presiding officer (use on-line script) | Contest Chair | [11 empty] | SF
12 | 12 | 42 | Brief the tie-breaking judge | Chief Judge | [11 empty] | SF |  |  |  | x
13 | 13 | 43 | Bring materials - folders, forms, etc. to the contest | Contest Chair | [12 empty] | SF
|  |  | Bring materials - folders, forms, etc. to the contest | Chief Judge | [12 empty] | SF
13 | 13 | 44 | Show up 45 minutes early. Set up the room | Contest Chair | [12 empty] | SF
13 | 13 | 45 | Find replacements if necessary | Contest Chair | [12 empty] | SF
|  |  | Check in attendees using the dignitary list and sign in sheet | Regis Chair | [12 empty] | SF
13 | 13 | 46 | Provide speaking area to the Chief Judge | Contest Chair | [12 empty] | SF
13 | 13 | 47 | Conduct Chief Judge Briefing | Chief Judge | [12 empty] | SF |  |  | x
13 | 13 | 48 | Conduct Contest Chair Briefing | Contest Chair | [12 empty] | SF |  |  | x
13 | 13 | 49 | Provide Eligibility and Originality forms to the Chief Judge | Contest Chair | [12 empty] | SF
|  |  | Give filled out dignitary list to Contest Chair | Regis Chair | [12 empty] | SF
13 | 13 | 50 | Call meeting to order, pledge and invocation, introductions | Contest Chair | [12 empty] | SF |  |  | x
13 | 13 | 51 | Introduce Toastmaster | Contest Chair | [12 empty] | SF
13 | 13 | 52 | Make mandatory announcements | Toastmaster | [12 empty] | SF |  |  | x
13 | 13 | 53 | Introduce Contestants, call for silence after speeches | Toastmaster | [12 empty] | SF |  |  | x
13 | 13 | 54 | Interview Contestants | Toastmaster | [12 empty] | SF |  |  | x
13 | 13 | 55 | Pick up Time Record Sheets, Tiebreaker ballot. Oversee ballot counting | Chief Judge | [12 empty] | SF |  |  | x
13 | 13 | 56 | Handle Eligibility protests | Contest Chair | [12 empty] | SF |  |  | x
13 | 13 | 57 | Handle Originality protests | Chief Judge | [12 empty] | SF |  |  | x
13 | 13 | 58 | Fill out Winner Announcement script, noting disqualification types | Chief Judge | [12 empty] | SF |  |  | x
|  |  | Fill out Winner Certificates | Chief Judge | [12 empty] | SF
13 | 13 | 59 | Make announcements, thank yous, announce awards, adjourn | Contest Chair | [12 empty] | SF
13 | 14 | 60 | Fill out Notification of Winners form. | Chief Judge | [12 empty] | SF |  |  | x
|  |  | Submit Contest results and contestant forms to next level Contest Chair | Contest Chair | [12 empty] | S | F |  | x
13 | 15 | 61 | Have a team member fill out Project #10 evaluation in your CL manual | Contest Chair | [12 empty] | S | x | F
14 | 15 | 62 | Write Thank-Yous to your team | Contest Chair | [13 empty] | S | F
14 | 15 | 63 | Write Thank-Yous to contest officials | Chief Judge | [13 empty] | S | F
15 | 15 | 64 | Celebrate having a well planned, organized, and executed contest! | Contest Chair | [14 empty] | SF
Have total confidence in yourself and your ability to pull this off
Commit to and envision a successful contest
Stay focused and organized
Meet with / encourage your team. Over-communicate and be certain
Be unwilling to compromise on what you need. Be consistent and firm
Be flexible as you get closer to the contest date (1 week out)
Re-confirm assignments / materials. Over-communicate and be certain
Legend
|  |  | Start of task |  | S
|  |  | Finish of task |  | F
|  |  | Continuation of task |  | x
Last Updated 6-24-2017

## Tasks
|  |  | Task List (sorted by due date) |  | 2019-09-12 |  |  | Put your club contest date into cell F1
Start | End | Seq | Task | Owner | Due Date |  | wks | Done? | Comments
1 | 2 | 1 | Select Contest Chair | VP Education | 2019-08-01 | 42 | 6
1 | 2 | 2 | Obtain Budget approval from Club Officers | Contest Chair | 2019-08-01 | 42 | 6
3 | 3 | 3 | Create To-do/checklist/timetable (use this as a guide) | Contest Chair | 2019-08-08 | 35 | 5
3 | 3 | 4 | Set date, time, and place. Hold contest in place of a regular meeting | Contest Chair | 2019-08-08 | 35 | 5
3 | 4 | 5 | Read ref. documents - http://www.tmd55.org/info-for-contest-organizers.html | Contest Chair | 2019-08-11 | 32 | 4.5
3 | 4 | 6 | Select Chief Judge | Contest Chair | 2019-08-11 | 32 | 4.5
3 | 4 | 7 | Select Awards Owner | Contest Chair | 2019-08-11 | 32 | 4.5
3 | 4 | 8 | Select Refreshments Owner | Contest Chair | 2019-08-11 | 32 | 4.5
4 | 11 | 12 | Promote the club contest with enthusiasm and optimism | Contest Chair | 2019-08-15 | 28 | 4
5 | 5 | 13 | Create a draft agenda | Contest Chair | 2019-08-15 | 28 | 4
5 | 5 | 14 | Train Chief Judge if necessary, and review tasks and ownership | Contest Chair | 2019-08-15 | 28 | 4
5 | 5 | 15 | Meet with Chief Judge to review tasks and ownership | Contest Chair | 2019-08-15 | 28 | 4
4 | 8 | 11 | Recruit and select judges. Network / trade with other clubs | Chief Judge | 2019-08-18 | 25 | 2.5
3 | 6 | 9 | Invite Toastmaster Dignitaries and Guests | Contest Chair | 2019-08-18 | 25 | 3.5
6 | 6 | 17 | Create a flier | Contest Chair | 2019-08-18 | 25 | 3.5
6 | 6 | 18 | Meet with Awards owner to plan gifts, awards, certificates and trophies | Contest Chair | 2019-08-18 | 25 | 3.5
5 | 7 | 16 | Select Toastmasters (one per contest) | Contest Chair | 2019-08-22 | 21 | 3
6 | 7 | 19 | Select Test Speaker (Evaluation Contest). Network with other clubs | Contest Chair | 2019-08-22 | 21 | 3
6 | 7 | 20 | Select Sergeants-at-Arms (need two) | Contest Chair | 2019-08-22 | 21 | 3
|  |  | Select Check-in / Registration chair (optional) | Contest Chair | 2019-08-22 | 21 | 3
6 | 7 | 21 | Select Ballot Counters (2-3) | Chief Judge | 2019-08-22 | 21 | 3
6 | 7 | 22 | Select Timers (2) | Chief Judge | 2019-08-22 | 21 | 3
3 | 8 | 10 | Order and receive or download contest materials from TI | Contest Chair | 2019-08-25 | 18 | 2.5
8 | 8 | 27 | Notify Contestants of Contest details; send rulebook and forms | Contest Chair | 2019-08-25 | 18 | 2.5
8 | 8 | 28 | Notify Contest Officials of Contest details (date, time, place) | Chief Judge | 2019-08-25 | 18 | 2.5
6 | 9 | 23 | Confirm judge eligibility. Find new judges as needed | Chief Judge | 2019-08-29 | 14 | 2
7 | 9 | 24 | Confirm contestant eligibility with TI | Contest Chair | 2019-08-29 | 14 | 2
7 | 9 | 25 | Order blank certificates | Awards Owner | 2019-08-29 | 14 | 2
7 | 10 | 26 | Order and receive or make trophies and gifts | Awards Owner | 2019-09-01 | 11 | 1.5
9 | 10 | 29 | Plan the Contestant briefing (use on-line script) | Contest Chair | 2019-09-01 | 11 | 1.5
9 | 10 | 30 | Plan the Chief Judge briefing (use on-line script) | Chief Judge | 2019-09-01 | 11 | 1.5
9 | 10 | 31 | Meet with the Refreshments owner to plan the refreshments | Contest Chair | 2019-09-01 | 11 | 1.5
9 | 11 | 32 | Train judges if necessary | Chief Judge | 2019-09-05 | 7 | 1
9 | 11 | 33 | Personalize on-line Toastmaster Script | Toastmaster | 2019-09-05 | 7 | 1
10 | 11 | 34 | Organize forms and awards into folders by person | Contest Chair | 2019-09-05 | 7 | 1
10 | 11 | 35 | Create/print/copy Agenda/Program document | Contest Chair | 2019-09-05 | 7 | 1
10 | 11 | 36 | Personalize certificates | Awards Owner | 2019-09-05 | 7 | 1
10 | 11 | 37 | Plan for miscellaneous items (e.g. stop watches). Materials tab | Contest Chair | 2019-09-05 | 7 | 1
10 | 12 | 38 | Reminder to Contestants | Contest Chair | 2019-09-08 | 4 | 0.5
10 | 12 | 39 | Reminder to Contest Officials | Chief Judge | 2019-09-08 | 4 | 0.5
12 | 12 | 41 | Prepare for your role as presiding officer | Contest Chair | 2019-09-08 | 4 | 0.5
12 | 12 | 42 | Brief the tie-breaking judge | Chief Judge | 2019-09-08 | 4 | 0.5
11 | 13 | 40 | Purchase and bring refreshments | Refresh Owner | 2019-09-12 | 0 | 0
13 | 13 | 43 | Bring materials - folders, forms, etc. to the contest | Contest Chair | 2019-09-12 | 0 | 0
|  |  | Bring materials - folders, forms, etc. to the contest | Chief Judge | 2019-09-12 |  | 0
13 | 13 | 44 | Show up 45 minutes early. Set up the room | Contest Chair | 2019-09-12 | 0 | 0
13 | 13 | 45 | Find replacements if necessary | Contest Chair | 2019-09-12 | 0 | 0
|  |  | Check in attendees using the dignitary list and sign in sheet | Regis Chair | 2019-09-12 | 0 | 0
13 | 13 | 46 | Provide speaking area to the Chief Judge | Contest Chair | 2019-09-12 | 0 | 0
13 | 13 | 47 | Conduct Chief Judge Briefing | Chief Judge | 2019-09-12 | 0 | 0
13 | 13 | 48 | Conduct Contest Chair Briefing | Contest Chair | 2019-09-12 | 0 | 0
13 | 13 | 49 | Provide Eligibility and Originality forms to the Chief Judge | Contest Chair | 2019-09-12 | 0 | 0
|  |  | Give filled out dignitary list to Contest Chair | Regis Chair | 2019-09-12 | 0 | 0
13 | 13 | 50 | Call meeting to order, pledge and invocation, guest introductions | Contest Chair | 2019-09-12 | 0 | 0
13 | 13 | 51 | Introduce Toastmaster | Contest Chair | 2019-09-12 | 0 | 0
13 | 13 | 52 | Make mandatory announcements | Toastmaster | 2019-09-12 | 0 | 0
13 | 13 | 53 | Introduce Contestants, call for silence after speeches | Toastmaster | 2019-09-12 | 0 | 0
13 | 13 | 54 | Interview Contestants | Toastmaster | 2019-09-12 | 0 | 0
13 | 13 | 55 | Pick up Time Record Sheets, Tiebreaker ballot. Oversee ballot counting | Chief Judge | 2019-09-12 | 0 | 0
13 | 13 | 56 | Handle Eligibility protests | Contest Chair | 2019-09-12 | 0 | 0
13 | 13 | 57 | Handle Originality protests | Chief Judge | 2019-09-12 | 0 | 0
13 | 13 | 58 | Fill out Winner Announcement script, noting disqualification types | Chief Judge | 2019-09-12 | 0 | 0
|  |  | Fill out Winner Certificates | Chief Judge | 2019-09-12 | 0 | 0
13 | 13 | 59 | Make announcements, thank yous, announce awards, adjourn | Contest Chair | 2019-09-12 | 0 | 0
|  |  | Fill out Notification of Winners form | Chief Judge | 2019-09-12 | 0 | 0
13 | 14 | 60 | Submit Contest results and contestant forms to Area Contest Owner | Contest Chair | 2019-09-16 | -4 | -0.5
13 | 15 | 61 | Have a team member fill out Project #10 evaluation in your CL manual | Contest Chair | 2019-09-19 | -7 | -1
14 | 15 | 62 | Write Thank-Yous to your team | Contest Chair | 2019-09-19 | -7 | -1
14 | 15 | 63 | Write Thank-Yous to contest officials | Chief Judge | 2019-09-19 | -7 | -1
15 | 15 | 64 | Celebrate having a well planned, organized, and executed contest! | Contest Chair | 2019-09-19 | -7 | -1
Last Updated 12-12-2017

## Materials
Materials Checklist
Materials to Contest | Responsible | Done? | Comments
Contest forms in folders; extra folders
Pens
Timing Indicators (minimum of 2)
Stopwatches (minimum of 2)
Calculators
Scissors
Draw for order
Envelopes
Awards
Certificates for volunteers
Refreshments
Lectern/podium
Gavel
Flag
Agendas
Scripts |  |  | http://www.tmd55.org/scripts.html
Toastmaster Script
Presiding Officer Script
Contest Chair Briefing Script
Chief Judge Briefing Script
Contest Winner Announcement Script
Dignitary List |  |  | http://www.tmd55.org/planning-documents.html
Sign in Sheet
Contest Forms |  |  | http://www.tmd55.org/forms-and-templates.html
Rulebooks
Judges Ballots
Judging Instructions
Timer Sheets
Ballot Counter Tally Sheets
Speaker Certifications
Contestant Biography Forms
Notification of Winner
Judge Certifications
Winner Certificates
Certificates of Participation
Last Updated 3-24-2015

## People Roles
People/Roles
Role | Name | Club(s) | Area | Cell Phone | Comments
Contest Chair
Awards Owner
Refreshments Owner
Registration Chair (optional)
Toastmaster (One per contest)
Toastmaster (One per contest)
Test Speaker (Eval Contest Only)
Chief Judge
Judge 1
Judge 2
Judge 3
Judge 4
Judge 5
Tie-Breaker Judge
Ballot Counter
Ballot Counter
Ballot Counter
Timer
Timer
Sergeant-at-Arms
Sergeant-at-Arms
Contest 1 | Name |  | Elig? | Cell Phone | Comments
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contest 2 | Name |  | Elig? | Cell Phone | Comments
Contestant
Contestant
Contestant
Contestant
Contestant
Contestant
Contest 1 | Name |  | Elig? | Cell Phone | Comments
Runner-Up
Runner-Up
Runner-Up
Runner-Up
Runner-Up
Runner-Up
Contest 2 | Name |  | Elig? | Cell Phone | Comments
Runner-Up
Runner-Up
Runner-Up
Runner-Up
Runner-Up
Runner-Up
Last Updated 12-12-2017

## Scope
Contest Elements
Speeches/Speakers
Judging/Judges
Contest Control/Chief Judge
Timing/Timers
Ballots/Ballot Counting
Toastmaster/Emcee
Awards/Presentation/Awards Maker
Contestant Interviews
Certificates of Participation
Thank-yous for Contest Officials
Room/Place
Time/Duration
Programs/Agenda
Room Control/Sergeants-at-Arms
Meeting Control/Presiding Officer
Refreshments/Refreshments Owner
Lots of Applause
Contest Team Lead/Project Management
Contest Notification/Promotion/Flier
Dignitaries
Briefings
Notification of Winners
Communication with Participants
Forms
Audience!
Last Updated 1/13/2013

## Contest Chair Briefing
Contest Chair Briefing Summary
Sergeant-at-Arms Briefing
Assist contestants with props and stage area
Manage room entry / exit during speeches
Evaluation contest
usher contestants to another room
pick up contestant notes after 5 minutes
escort contestants into meeting room one at a time
Table Topics Contest
usher all contestants but first contestant to another room
escort remaining contestants into meeting room one at a time
Contestant Briefing
Receive bio forms - give to Toastmaster
Receive Certification of Eligibiilty / Originality forms - give to Chief Judge
Draw for speaking order
Define / illustrate speaking area
Define the staging area (place where contestants stand just prior to being introduced)
Go over each contestant's speaking area and prop requirements
Review the timing rules and timing signals. Point out the location of the timers
Have each contestant pronounce his/her name for benefit of Toastmaster
Have each speech contestant pronounce the title of his/her speech
Review Protest Process
Toastmaster Briefing
Confirm use and preparation of the script
Confirm speaking order and titles
Confirm pronunciation of contestant names
Confirm proper speaker introduction for each speech contest type
For Table Topics contest, provide Topic, confirm pronunciation of the Topic
Confirm receipt of speaker bios
The above is a synopsis of the briefing. Please refer to the actual briefing document
found on the District 55 website contest page for more detail and the lastest information
Last Updated 11/22/2013

## Chief Judge Briefing
Chief Judge Briefing Summary
Judge Briefing (Tie-breaking Judge is briefed separately)
Distribute folders with Judges Guides and Ballots, and Rulebook
Collect Judge Certification forms
Ask judges to sign the ballots
Instruct the judges on the use of the Guide and Ballot forms
Review the Fairness items
Review the Protest process
Timer Briefing
Assign Timer 1 to run the official stopwatch and fill out the Time Record Sheet
Assign Timer 2 to run the backup stopwatch and provide the timing signals
Review when to start the stopwatch
Review the timing signal rules for each contest
Provide instructions on providing the timing signal until the next timing signal
Ballot Counter Briefing
Space yourselves apart in the room when it is time to collect ballots
Hand ballots to the Chief Judge when they have all been collected
Verify that all ballots are good (signed, all places listed)
Do not tally score for disqualified contestants
Each counter fills out a Counter Tally sheet
Judges on the rows, Contestants on the columns
3 points for 1st place, 2 points for 2nd place, 1 point for third place
Add up the points for each contestant, then compare results with other counters
Resolve any discrepancies and break any ties using the tie-breaker judge ballot
Write down the 1st, 2nd, and 3rd place winners
If winner announcement is incorrect, immediately interrupt the announcement
The above is a synopsis of the briefing. Please refer to the actual briefing document
found on the District website contest page for more detail and the lastest information
Last Updated 1/4/2013